## PMBOK-Guide-Daily-activities
K.A. | Initiating Process | Planning Process | Executing Process | Monito & Contro Process | Closing Process
Integration | MSA/Project Contract/SOW/ Project creation, numbering, templates, Past project references,Test Cases. | Entire Project plan, Project Log, People Log. What are the project assumptions. Top level risks in the project - PM's list of personal docs | Actual project Execution | Check progress/status | Project handover, production support, warranties.
Scope |  | Collect requirement, define scope and creating wbs with PO | CR & Business case. | Project Demo(validation). CR & Business case.
Time |  | Define project activities, Estimate resources, Resource breakdown structure and schedule. |  | Check project schedule/milestones/Delays if any.
Cost |  | Opex, Budget, Costing, Project P&L. | Progress report, statuses/RAG. Time to complete. | Progress report, statuses/RAG. Time to complete. | P&L, Actual margins, Actual Revenue recognisition, invoicing, payments. Project metrics - budget v/s spend. Post mortem.
Quality |  | Quality Audits. Report audit findings | Quality Audits. Report audit findings | Quality Audits. Report audit findings | Final Audit. KT. Knowledge sharing sessions, and creation of repository. Test Cases, test bank.
HR |  | Plan for Hiring, Retention, Project Onboarding. Assimliation, Training. | Hiring, Retention, Project Onboarding. Assimliation, Training. Team building. | Hiring, Retention, Project Onboarding. Assimliation, Training. Team building. | Project Appraisals, feedback. Project release. Project rewards, recognisitions.
Communication |  | Point of Contact | Point of Contact | Point of Contact | Point of Contact
Risk |  | Creating of Risk register. Identify, watch, monitor and report. | Identify, watch, monitor and report - Risk | Identify, watch, monitor and report Risk.
Procurement |  | IT HW, SW - Licenses, | IT HW, SW - Licenses, | IT HW, SW - Licenses, | Close contingent workers. Licenses. Return h/w
Stakeholder | Identify all stakeholders within the project and at client. | Progress review schedule, Plan for steeering Committee meetings | Update progress, client meetings, weekly calls. steeering Committee meetings. Customer Feedback | Update progress, client meetings, weekly calls. steeering Committee meetings. Customer Feedback | Customer feedback and satisfaction Survey. Publishing satisfaction score.

## Phases-of-PM-Activities
Project Management activities
RFP /Q Stage
| Activities | Description | Involvement
| Commercial input | 1. Manhours rate, blended rate 2. Resources inhouse capability & capacity | Self
| Budget | 1. People 2. Developmet offshore/onshore, 4. IT H/w & S/W licenses, GOM > 65% | Self
| Agreement and Contracts | 1. Review contract T&C, 2. Post delivery-warranties, 3. Production support, 4. External audits, 5. Performance guarantee, penalty clauses, bank guarantee. | Presales + Self
| Client Meeting | 1. Understanding project, 2. Financial implications. | Self + Technical Team + Presales
| Technical Capability | Project technical summary. Ensure replete with case studies. Incorporate customer feedback. | Presales + Technical Team
Early Engineering (A good PM practices)
| Activities | Description | Involvement
| Identify resources, Procurements | 1. Identify lead resources. 2. Project training 3. Project warm up session. | Self
Win Confidence level > 75% | Identify Risk, Assumptions | 1. Past project risks, 2. Research, 3. SME's. | Technical team
| Templates | 1. Project templates. 2. Creation of project environment. | Technical team
| Project Execution Methodology |  | Technical team
| Procurements | 1. Identify & initiate procurements, 2. Identify vendors, get quotes, delivery time. | Self
| Deliverables | 1. Identify possible features/deliverables, 2. Demo's. 3. Trail run project on MS Project using Gantt chart. | Technical team
| Contracts | 1. Contract conditions, work with attorneys, 2. Prepare SOW, 3. Payment terms (if any BG, penalty clauses) | Self
Project Execution
| Activities | Description | Involvement
| Project Road Map | Project Goals, obj, timelines, imp milestones, deliverables, features, possible risk, assumptions, dependencies | Self
| Kick Off Meeting | Technicals + expectations setting. | All
| Workshop | 1. Workshops to ideate and Wishlist, identify additional risks, assumptions and dependencies. 2. Project expectations and deliverables. 3. Status and progress reporting, reviews. 4. Escalations | Self + Technical Team
| Project Cost | 1. Opex, 2. Cost of resources, 3. P&L. | Self
| Communication | 1. POC to all Stakeholders. 2. Progress reports/statues, RAG report. | Self
| Business Case | 1. Justification for CR/, 2. Additional procurement in-between project | Self + Technical Team
| Metrics | Earned Value, Time to complete, budget v/s spend, Utilization, risk, defects | Self
| Procurement | 1. Contingent workers, 2. SME/Testing Companies, 3. IT HW-SW Licenses | Self + IT + Admin
| Compliance | 1. Timesheet, 2. Audits, 3. Checking for Scope + Time + Budget, 4. Contractual compliance. 5. Compliance to org policies. 6. Compliant to contracts/agreement/MSA. | Self
| Governance | 1. Project structure, reporting mechanism, roles and responsibilities, 2. Regular & timely communication to Clients&Stakeholders. Steering Committee meetings. | Self
Client Collaboration
| Activities | Description | Involvement
| Workshop | 1. Workshops to ideate and Wishlist, identify additional risks, assumptions and dependencies. 2. Project expectations and deliverables. 3. Status and progress reporting, reviews. 4. Escalations | Self
| PI Planning | 1. Organise Project initiation meeting (PI) planning. 2. Setting up sprint calendar and schedule. 3. Assisting in Jira story, Jira Kanban board. | Self
| Scrum meetings | Conduct scrum meetings in the absence of PO and Client. | Self
| Progress review | Report Progress, statuses, Audit findings, Compliances and Governances | Self
Internal Stakeholders
| Activities | Description | Involvement
| Technical Team | 1. Capacity Planning, skill building, 2. People onboarding, project ready resources, 3. Ttechnical engagements. 4. Rewards & Recognitions. | Self
| Recruitment | Hiring inputs, evaluations. Project onboarding | Self
| HR | Retention, year end appraisal, project completion appraisal, compenation review. | Self
| Training | 1. Organise Training internally. 2. As part of product procurement - training sessions. | Self
| IT Infra team | New systems, setting up project environment, SharePoint access, VPN, access controls. | Self
| Mobility Team | Business ready travel, visa and travel policy | Self
| Finance Team | Project funds, report utilization for invoicing. Cash flow projections | Self