## Phases-of-PM-Activities
Project Management activities
RFP /Q Stage
| Activities | Description | Involvement
| Commercial input | Manhours rate, blended rate. | Self
| Budget | People required, offshore/onshore deve., Travel, S/W licenses, GOM > 65% | Self
| Agreement and Contracts | Review contract T&C, post delivery-warranties, production support, external audits, Bank Guarantee, penalty clauses, performance guarantee. | Presales + Self
| Client Meeting | Understanding project, financial implications. | Self + Technical Team + Presales
| Technical Capability | Project technical summary. Ensure replete with case studies. Incorporate customer feedback. | Presales + Technical Team
Early Engineering (A good PM practices)
| Activities | Description | Involvement
| Identify resources, Procurements | Identify lead resources. Initial training. Project warm up. | Self
Win Confidence level > 75% | Identify Risk, Assumptions | Past project risks, Research, SME's. | Technical team
| Templates | Project templates. Creation of project environment. | Technical team
| Project Execution Methodology |  | Technical team
| Procurements | Identify & initiate procurements, Identify vendors, get quotes, delivery time. | Self
| Deliverables | Identify deliverables, features, demo's. Trail run on MS Project. | Technical team
| Contracts | Contract conditions, work with attorneys, prepare SOW, payment terms, BG, penalty clauses. | Self
Project Execution
| Activities | Description | Involvement
| Project Cost | Opex, cost of resources, P&L. | Self
| Project Road Map | Project Goals, obj, timelines, imp milestones, deliverables, features, possible risk, assumptions, dependencies | Self
| Kick Off Meeting | Technicals + expectations setting. | All
| Workshop | Workshops to ideate and Wishlist, identify additional risks, assumptions and dependencies. Project expectations setting and deliverables. Status and progress reporting, reviews. Escalations | Self + Technical Team
| Communication | POC to all Stakeholders. Progress reports/statues, RAG report. | Self
| Business Case | Justification for CR/, additional procurement in-between project | Self + Technical Team
| Metrics | Earned Value, Time to complete, budget v/s spend, Utilization, risk, defects | Self
| Procurement | Contingent workers, SME/Testing Companies, IT HW-SW Licenses | Self + IT + Admin
| Compliance | Timesheet, Audits, Checking for Scope + Time + Budget, Contractual compliance. Compliance to org policies. Compliant to contracts/agreement/MSA. | Self
| Governance | Project structure, reporting mechanism, roles and responsibilities, Regular & timely communication to Clients&Stakeholders. Steering Committee meetings. | Self
Client Collaboration
| Activities | Description | Involvement
| Workshop | Workshops to ideate and Wishlist, identify additional risks, assumptions and dependencies. Project expectations setting and deliverables. Status and progress reporting, reviews. Escalations | Self
| PI Planning | Organise Project initiation meeting (PI) planning. Setting up sprint calendar and schedule. Assisting in Jira story, Jira Kanban board. | Self
| Scrum meetings | Conduct scrum meetings in the absence of PO and Client. | Self
| Progress review | Report Progress, statuses, Audit findings, Compliances and Governances | Self
Internal Stakeholders
| Activities | Description | Involvement
| Technical Team | Capacity Planning, skill building, people onboarding, project ready resources, technical engagements. Rewards & Recognitions. | Self
| Recruitment | Hiring inputs, evaluations. Project onboarding | Self
| HR | Retention, year end appraisal, project completion appraisal, Comp review. | Self
| Training | Project training for people who are deployed to project | Self
| IT Infra team | New systems, setting up project environment, SharePoint access, VPN, access controls. | Self
| Mobility Team | Business ready travel, visa and travel policy | Self
| Finance Team | Project funds, report utilization for invoicing. Cash flow projections | Self

## PMBOK-Mapped
| Initiating | Planning | Executing | M&C | Closing
Integration | MSA/Project Contract/SOW/ Project creation, numbering, templates, Past project references,Test Cases. | Entire Project plan, Project Log, People Log. What are the project assumptions. Top level risks in the project - PM's list of personal docs | Actual project Execution | Check progress/status | Project handover, production support, warranties.
Scope |  | Collect requirement, define scope and creating wbs with PO | CR & Business case. | Project Demo(validation). CR & Business case.
Time |  | Define project activities, Estimate resources, Resource breakdown structure and schedule. |  | Check project schedule/milestones/Delays if any.
Cost |  | Opex, Budget, Costing, Project P&L. | Progress report, statuses/RAG. Time to complete. | Progress report, statuses/RAG. Time to complete. | P&L, Actual margins, Actual Revenue recognisition, invoicing, payments. Project metrics - budget v/s spend. Post mortem.
Quality |  | Quality Audits. Report audit findings | Quality Audits. Report audit findings | Quality Audits. Report audit findings | Final Audit. KT. Knowledge sharing sessions, and creation of repository. Test Cases, test bank.
HR |  | Plan for Hiring, Retention, Project Onboarding. Assimliation, Training. | Hiring, Retention, Project Onboarding. Assimliation, Training. Team building. | Hiring, Retention, Project Onboarding. Assimliation, Training. Team building. | Project Appraisals, feedback. Project release. Project rewards, recognisitions.
Communication |  | Point of Contact | Point of Contact | Point of Contact | Point of Contact
Risk |  | Creating of Risk register. Identify, watch, monitor and report. | Identify, watch, monitor and report - Risk | Identify, watch, monitor and report Risk.
Procurement |  | IT HW, SW - Licenses, | IT HW, SW - Licenses, | IT HW, SW - Licenses, | Close contingent workers. Licenses. Return h/w
Stakeholder | Identify all stakeholders within the project and at client. | Progress review schedule, Plan for steeering Committee meetings | Update progress, client meetings, weekly calls. steeering Committee meetings. Customer Feedback | Update progress, client meetings, weekly calls. steeering Committee meetings. Customer Feedback | Customer feedback and satisfaction Survey. Publishing satisfaction score.